## Fund Accountability Statement
Birat Nepal Medical Trust- BNMT Nepal
Lazimpat-Kathmandu, Nepal
Fund Accountability Statement
Project: Nepali Drone Observed Therapy Systms Pilot: Improving Tuberculosis Case-Finding and Diagnostics with Drones
For the Period of: October 1, 2018 to December 31, 2018
Details | Amount- USD | Amount- USD
Income
Opening Balance | 0
Fund Received During the Period | 69910
Total Income (A) |  | 69910
Expenditure
Programme Activities | 9191
Visibility Materials | 0
Monitoring and Supervision | 0
Human Resource Cost | 9727.4547
Office Equipments | 0
Laboratory/HR Strengthening | 0
Programme Management Admin-Central | 0
Programme Management Admin-Field | 0
Overhead | 1891.8846
Total Expenditure (B) |  | 20810.3393
Fund Balance ( C )= A-B |  | 49099.6607
Plan for Next Quarter (D) |  | 89099.9
Fund Request for Next Period ( E )=D-C |  | 40000.2393
Prepared By: |  | Approved By
Laxmi Prasad Dahal |  | Suman Chandra Gurung
Finance Manager |  | Executive Director

## Budget Vs Exp
Birat Nepal Medical Trust
Lazimpat-Kathmandu
Budget Vs Expenditrue Statement- Details
Project Period: October 2018 to June 2019
Reporting Period: October 2018 to December 2018
Project: Nepali Drone Observed Therapy Systms Pilot: Improving Tuberculosis Case-Finding and Diagnostics with Drones
Budget Head | Total Budget |  |  | Expenditure |  |  | Utilization % | Remarks
| Pre. Period | Imp. Period | Total | Prev. Period | Current Period | Total
Programme Activities
Consultative meeting with NTC | 135 |  | 135 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Consultative meeting with MoH | 108 |  | 108 | 0 | 65.6923 | 65.6923 | 60.83%
Planning/Review meeting with MOH/NTC | 0 | 370 | 370 | 0 |  | 0 | 0% | 2nd Phase
Consultative meeting with Local Bodies | 1144 |  | 1144 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Consultative meeting with Selected DHO/HFs/DOTs Center/MC/GeneXpert Center | 1575 |  | 1575 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Planning/Sharing Meeting with Local Body/Health Facilities and other concerned stakeholders | 0 | 1983 | 1983 | 0 |  | 0 | 0% | 2nd Phase
Ethical Approval from NHRC | 4808 |  | 4808 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Project Agreement with MoH/SWC/Local Body | 296 |  | 296 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Kick Off Meeting | 0 | 5853 | 5853 | 0 |  | 0 | 0% | 2nd Phase
SOP Workshop | 5853 |  | 5853 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Training/Orientation with Existing Volunteers/Mobilisors | 2260 |  | 2260 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Assesment of Microscopic Center/GeneXpert Center | 8769 |  | 8769 | 0 | 8769 | 8769 | 100% | Expenditure not incurred due to delay approval from Nepal Government
Training of staff involved at each step of the DrOTS process (flying, suspect case identification, laboratory diagnostics, data management). | 4005 |  | 4005 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Door to Door Sputum Collection | 9375 | 13918.5 | 23293.5 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Mobilization of Lab Personnel | 1243.2 | 898.5 | 2141.7 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Developed and Printing Forms/Formates for Data Collections | 1010 | 1010 | 2020 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Procured Lab and Sputum Related Materials | 11466 | 5733 | 17199 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Procured Tablet/Mobile for data collection | 635 | 288 | 923 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Orientation/Training to Data Management | 1976 |  | 1976 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Procured GeneXpert Machine | 96 |  | 96 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Repair and Maintenance Microscopes and Supplies | 962 | 240.5 | 1202.5 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Identificaton and Screening of Index Cases for Contact Tracing in District | 2529.6 | 6644.4 | 9174 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Mobilization of community Mobilizer | 5077.2 | 2538.5 | 7615.7 | 0 |  | 0 | 0% | Expenditure not incurred due to delay approval from Nepal Government
Benchtop Centrifuge for Xtrapulm Samples at Pyuthan Hospital | 0 | 2000 | 2000 | 0 | 356.3077 | 356.3077 | 17.82%
| 63323 | 41477.4 | 104800.4 | 0 | 9191 | 9191 | 8.77%
Visibility Materials
Developed and Printing of Visibility Materials | 457 | 457 | 914 | 0 |  | 0 | 0%
Translation and Printing Cost of MERMS Documents | 1106 |  | 1106 | 0 |  | 0 | 0%
| 1563 | 457 | 2020 | 0 | 0 | 0 | 0% | 0
Monitoring and Supervision
Field Monitoring-Field Level Staff | 1010.4 | 2019 | 3029.4 | 0 |  | 0 | 0%
Joint Monitoring Visit With NTC/MoH/BNMT/Local Bodies/DHO | 2260 | 3245 | 5505 | 0 |  | 0 | 0%
MERMS Experience Review Meeting with CMs, FCHVs, Volunteers and Programme Personnel | 5576 |  | 5576 | 0 |  | 0 | 0%
Review Meeting at Field Stakeholders |  | 892 | 892 | 0 |  | 0 | 0%
Review/Further Planning Meeting at National Stakeholders |  | 654 | 654 | 0 |  | 0 | 0%
| 8846.4 | 6810 | 15656.4 | 0 | 0 | 0 | 0% | 0
Human Resource Cost
Project Manager | 2885 | 1442.5 | 4327.5 | 0 | 678.6599 | 678.6599 | 15.68%
District Co-Ordinator | 4038 | 2019 | 6057 | 0 | 1124.0006 | 1124.0006 | 18.56%
LSTM-Senior TB Researcher | 12000 | 6000 | 18000 | 0 | 6000 | 6000 | 33.33%
Executive Director | 1442 | 1081.5 | 2523.5 | 0 | 966.5391 | 966.5391 | 38.3%
Knowledge Management Manager | 891 | 148.5 | 1039.5 | 0 | 415.0995 | 415.0995 | 39.93%
Finance Manager | 1188 | 445.5 | 1633.5 | 0 | 434.5221 | 434.5221 | 26.6%
HR/Admin Manager | 297 | 148.5 | 445.5 | 0 | 108.6335 | 108.6335 | 24.38%
Office Assistant/Support Staff | 0 | 432.5 | 432.5 | 0 | 0 | 0 | 0%
Admin/Finance/Logistic Assistant | 0 | 865.5 | 865.5 | 0 | 0 | 0 | 0%
Staff Settelement Cost | 359 |  | 359 | 0 | 0 | 0 | 0%
| 23100 | 12583.5 | 35683.5 | 0 | 9727.4547 | 9727.4547 | 27.26% | 0
Office Equipments
Laptop with asses. | 962 |  | 962 | 0 |  | 0 | 0%
Office Furniture |  | 962 | 962 | 0 |  | 0 | 0%
Motorcycle with Asses. |  | 2403 | 2403 | 0 |  | 0 | 0%
| 962 | 3365 | 4327 | 0 | 0 | 0 | 0% | 0
Laboratory/HR Strengthening |  | 5000 | 5000 | 0 |  | 0 | 0%
Programme Management Admin-Central | 1183 | 2014.5 | 3197.5 | 0 |  | 0 | 0%
Programme Management Admin-Field |  | 1880 | 1880 | 0 |  | 0 | 0%
Overhead | 10553 | 10173 | 20726 | 0 | 1891.8846 | 1891.8846 | 9.128%
Total | 109530.4 | 83760.4 | 193290.8 | 0 | 20810.3393 | 20810.3393 | 10.77% | 0

## Plan for Next Period
Birat Nepal Medical Trust
Lazimpat-Kathmandu
Budget Vs Expenditrue Statement- Details
Project Period: October 2018 to June 2019
Reporting Period: October 2018 to December 2018
Project: Nepali Drone Observed Therapy Systms Pilot: Improving Tuberculosis Case-Finding and Diagnostics with Drones
Budget Head | Budget | Expenditure | Next Qtr | Budget Balance | Utilization % | Remarks
| Total | Total | Plan
Programme Activities
Consultative meeting with NTC | 135 | 0 | 135 | 0 | 100%
Consultative meeting with MoH | 108 | 65.6923 | 42 | 0.30769 | 99.72%
Planning/Review meeting with MOH/NTC | 370 | 0 | 0 | 370 | 0%
Consultative meeting with Local Bodies | 1144 | 0 | 1144 | 0 | 100%
Consultative meeting with Selected DHO/HFs/DOTs Center/MC/GeneXpert Center | 1575 | 0 | 1575 | 0 | 100%
Planning/Sharing Meeting with Local Body/Health Facilities and other concerned stakeholders | 1983 | 0 | 0 | 1983 | 0%
Ethical Approval from NHRC | 4808 | 0 | 4808 | 0 | 100%
Project Agreement with MoH/SWC/Local Body | 296 | 0 | 296 | 0 | 100%
Kick Off Meeting | 5853 | 0 | 0 | 5853 | 0%
SOP Workshop | 5853 | 0 | 5853 | 0 | 100%
Training/Orientation with Existing Volunteers/Mobilisors | 2260 | 0 | 2260 | 0 | 100%
Assesment of Microscopic Center/GeneXpert Center | 8769 | 8769 | 0 | 0 | 100%
Training of staff involved at each step of the DrOTS process (flying, suspect case identification, laboratory diagnostics, data management). | 4005 | 0 | 4005 | 0 | 100%
Door to Door Sputum Collection | 23293.5 | 0 | 9375 | 13918.5 | 40.25%
Mobilization of Lab Personnel | 2141.7 | 0 | 1243.2 | 898.5 | 58.05%
Developed and Printing Forms/Formates for Data Collections | 2020 | 0 | 1010 | 1010 | 50%
Procured Lab and Sputum Related Materials | 17199 | 0 | 11466 | 5733 | 66.67%
Procured Tablet/Mobile for data collection | 923 | 0 | 635 | 288 | 68.8%
Orientation/Training to Data Management | 1976 | 0 | 1976 | 0 | 100%
Procured GeneXpert Machine | 96 | 0 | 96 | 0 | 100%
Repair and Maintenance Microscopes and Supplies | 1202.5 | 0 | 962 | 240.5 | 80%
Identificaton and Screening of Index Cases for Contact Tracing in District | 9174 | 0 | 2529.6 | 6644.4 | 27.57%
Mobilization of community Mobilizer | 7615.7 | 0 | 5077.2 | 2538.5 | 66.67%
Benchtop Centrifuge for Xtrapulm Samples at Pyuthan Hospital | 2000 | 356.3077 | 0 | 1643.6923 | 17.82%
| 104800.4 | 9191 | 54488 | 41121.4 | 60.76%
Visibility Materials
Developed and Printing of Visibility Materials | 914 | 0 | 457 | 457 | 50%
Translation and Printing Cost of MERMS Documents | 1106 | 0 | 1106 | 0 | 100%
| 2020 | 0 | 1563 | 457 | 77.38% | 0
Monitoring and Supervision
Field Monitoring-Field Level Staff | 3029.4 | 0 | 1010.4 | 2019 | 33.35%
Joint Monitoring Visit With NTC/MoH/BNMT/Local Bodies/DHO | 5505 | 0 | 2260 | 3245 | 41.05%
MERMS Experience Review Meeting with CMs, FCHVs, Volunteers and Programme Personnel | 5576 | 0 | 5576 | 0 | 100%
Review Meeting at Field Stakeholders | 892 | 0 | 0 | 892 | 0%
Review/Further Planning Meeting at National Stakeholders | 654 | 0 | 0 | 654 | 0%
| 15656.4 | 0 | 8846.4 | 6810 | 56.5% | 0
Human Resource Cost
Project Manager | 4327.5 | 678.6599 | 1442.5 | 2206.3401 | 49.02%
District Co-Ordinator | 6057 | 1124.0006 | 2019 | 2913.9994 | 51.89%
LSTM-Senior TB Researcher | 18000 | 6000 | 6000 | 6000 | 66.67%
Executive Director | 2523.5 | 966.5391 | 967 | 589.9609 | 76.62%
Knowledge Management Manager | 1039.5 | 415.0995 | 415 | 209.4005 | 79.86%
Finance Manager | 1633.5 | 434.5221 | 435 | 763.9779 | 53.23%
HR/Admin Manager | 445.5 | 108.6335 | 109 | 227.8665 | 48.85%
Office Assistant/Support Staff | 432.5 | 0 | 0 | 432.5 | 0%
Admin/Finance/Logistic Assistant | 865.5 | 0 | 0 | 865.5 | 0%
Staff Settelement Cost | 359 | 0 | 359 | 0 | 100%
| 35683.5 | 9727.4547 | 11746.5 | 14209.5453 | 60.18% | 0
Office Equipments
Laptop with asses. | 962 | 0 | 962 | 0 | 100%
Office Furniture | 962 | 0 | 962 | 0 | 100%
Motorcycle with Asses. | 2403 | 0 | 691 | 1712 | 28.76%
| 4327 | 0 | 2615 | 1712 | 60.43% | 0
Laboratory/HR Strengthening | 5000 | 0 | 0 | 5000 | 0%
Programme Management Admin-Central | 3197.5 | 0 | 1183 | 2014.5 | 37%
Programme Management Admin-Field | 1880 | 0 | 0 | 1880 | 0%
Overhead | 20726 | 1891.8846 | 8658 | 10176.1154 | 50.9%
Total | 193290.8 | 20810.3393 | 89099.9 | 83380.5607 | 56.86%